Prepared from the operations export and the 2026-09-30 decision

# Decision

The steering group approved a two-week follow-up pilot, not a full rollout.

# Evidence

- Request volume rose from 80 to 100 per day (+25%).

- Median response time fell from 12 to 9 hours (−25%).

- Error rate rose from 2% (8 of 400) to 3% (15 of 500).

# Risks

The comparison is observational: there was no random allocation and the customer mix differs, so the improvement is not causal evidence. The error rate rose.

# Next steps

Ownership

| Owner | Budget | Final review |
| --- | --- | --- |
| Maya Okafor | EUR 2,400 | 2026-10-19 |

Stop the follow-up pilot if the error rate exceeds 4 percent.