# Meridian pilot — FAQ

## What did the pilot measure?

Requests rose from 80 to 100 per day (+25%) and the median response time fell from 12 to 9 hours.

## Did errors change?

Yes. The error rate went from 2% (8 of 400) to 3% (15 of 500).

## Was a full rollout approved?

No. A two-week follow-up pilot was approved, owned by Maya Okafor, with a budget of EUR 2,400.

## When does the follow-up stop?

If the error rate exceeds 4 percent. The final review is on 2026-10-19.

## Is the improvement causal?

No. There was no random allocation and the groups differ.